# ROADMAP & TIMELINE

TesteoLab - 4 Fases de Desarrollo

Fecha: 10 de Abril, 2026

# Visión General del Proyecto

TesteoLab se construye en 4 fases estratégicas de 24-28 semanas totales:

FASE 1 (MVP) - SEMANAS 1-10: Módulo 3 + Infrastructure Core
├─ Objetivo: Validar core value proposition (generación de creatives)
├─ Alcance: M3 completo con 8 pasos, integración Midjourney & Veo 3.1
├─ Entrada de datos: Manual + Mock data
├─ Usuarios: Internal testers + early adopters
└─ Outcome: Plataforma mínima viable generando creatives de calidad

FASE 2 (EXPAND) - SEMANAS 11-18: Módulos 1 & 4 + Meta Integration
├─ Objetivo: Cerradura el loop completo: research → creatives → campaigns
├─ Alcance: M1 (Espionaje) + M4 (Seguimiento), Meta Ads API integration
├─ Entrada de datos: Real Meta Ads Library data
├─ Usuarios: Private beta group (50-100 users)
└─ Outcome: Plataforma end-to-end con research y campaign tracking

FASE 3 (COMPLETION) - SEMANAS 19-23: Módulo 2 + Polish
├─ Objetivo: Completar todos 4 módulos, mejorar UX/performance
├─ Alcance: M2 (Creación de Oferta), refinements de M1-4
├─ Entrada de datos: Full user data, multi-language support
├─ Usuarios: Closed beta (200-500 users), ready for launch
└─ Outcome: Plataforma completa, feature-rich, production-ready

FASE 4 (LAUNCH & OPTIMIZE) - SEMANAS 24-28: Go-Live & Growth
├─ Objetivo: Lanzar al público, on-board early customers
├─ Alcance: Marketing, sales enablement, customer support
├─ Entrada de datos: Todos los usuarios, datos en producción
├─ Usuarios: Public beta → public launch
└─ Outcome: TesteoLab publicly available, generating revenue

TIMELINE TOTAL: 28 semanas (~6.5 meses)
Inicio estimado: Abril 2026
Go-live estimado: Octubre 2026

# FASE 1: MVP - MÓDULO 3 & INFRASTRUCTURE

Duración: 10 semanas | Hito final: MVP con Módulo 3 funcional

## Objetivos Clave

Construir arquitectura base de Supabase (28 tablas)

Implementar autenticación y multi-tenancy (users, projects)

Desarrollar front-end core (Next.js + React + Tailwind)

Integrar 5 agentes (Asistente Guía, Marketing, Código, Leads, Planificación)

Completar M3 con 8 pasos interactivos

Integración API con Midjourney y Veo 3.1

Sistema de language selectors (UI + Generation)

Dashboard inicial para visualizar creatives generados

## Desglose por Semana

SEMANAS 1-2: FOUNDATION & SETUP (Backend Infrastructure)
├─ Tarea 1: Configurar Supabase project
│  ├─ Crear 28 tablas con relaciones
│  ├─ Implementar RLS policies
│  ├─ Índices y optimización inicial
│  └─ Time: 3 days
├─ Tarea 2: Setup autenticación
│  ├─ Auth flows (signup, login, logout)
│  ├─ JWT tokens, refresh tokens
│  ├─ Multi-tenancy architecture
│  └─ Time: 2 days
├─ Tarea 3: Ciencia base de datos
│  ├─ Tablas GLOBAL (users, subscriptions, projects)
│  ├─ Tablas M3 (creative_research, angles, styles, etc.)
│  ├─ Relaciones y constraints
│  └─ Time: 4 days
├─ Tarea 4: API base setup
│  ├─ Next.js API routes
│  ├─ Middleware de autenticación
│  ├─ Error handling, logging
│  └─ Time: 3 days
└─ DELIVERY: Working Supabase + Auth backend (API testable via curl)

SEMANAS 2-3: FRONT-END CORE & PROJECT SETUP
├─ Tarea 1: Front-end architecture
│  ├─ Next.js project setup
│  ├─ React components structure
│  ├─ Tailwind CSS theming
│  └─ Time: 2 days
├─ Tarea 2: Auth UI flows
│  ├─ Login page
│  ├─ Signup flow
│  ├─ Project creation/selection
│  └─ Time: 3 days
├─ Tarea 3: Project dashboard skeleton
│  ├─ Navigation/sidebar
│  ├─ Module selector (M1-M4)
│  ├─ Settings page (language selectors)
│  └─ Time: 2 days
├─ Tarea 4: Language settings system
│  ├─ Dual language selectors (UI + Generation)
│  ├─ Language variant support (español rioplatense)
│  ├─ I18n integration
│  └─ Time: 2 days
└─ DELIVERY: Fully functional auth + dashboard + language system

SEMANAS 4-6: MÓDULO 3 STEPS 1-4 (Steps: Extracción, Identidad, Estilo, Formatos)
├─ Tarea 1: STEP 1 - Extracción (Week 4)
│  ├─ UI form para seleccionar data de M1/M2
│  ├─ Data visualization (cards, tags)
│  ├─ Validation flow
│  ├─ Backend: creative_research table + endpoints
│  └─ Time: 3 days
├─ Tarea 2: STEP 2 - Identidad (Week 4-5)
│  ├─ UI forms: misión, visión, valores, tono
│  ├─ Multi-select components
│  ├─ AI-powered suggestion system (mock initially)
│  ├─ Backend: store identity data
│  └─ Time: 4 days
├─ Tarea 3: STEP 3 - Estilo Visual (Week 5)
│  ├─ Color picker component
│  ├─ Aesthetic radio buttons
│  ├─ Live preview de estilos
│  ├─ Backend: visual_styles table + endpoints
│  └─ Time: 3 days
├─ Tarea 4: STEP 4 - Formatos (Week 5-6)
│  ├─ Format checkboxes (carousel, single, video, reel, story, collection)
│  ├─ Spec inputs (dimensiones, duración, cantidad)
│  ├─ Dynamic summary calculator
│  ├─ Backend: creative_formats table + validation
│  └─ Time: 3 days
└─ DELIVERY: Steps 1-4 fully interactive en UI

SEMANAS 6-8: MÓDULO 3 STEPS 5-6 + AGENT INTEGRATION (Análisis IA, Ángulos)
├─ Tarea 1: Agent Infrastructure
│  ├─ Agent orchestration system
│  ├─ Prompt templates para todos los agents
│  ├─ Logging system (agent_logs table)
│  ├─ Queue system (generation_queue table)
│  └─ Time: 4 days
├─ Tarea 2: STEP 5 - Análisis IA (Week 6-7)
│  ├─ UI: Loading state + results display
│  ├─ Agente Marketing API calls (Claude)
│  ├─ Insights visualization (cards, charts)
│  ├─ Backend: ad_analysis table + endpoints
│  └─ Time: 4 days
├─ Tarea 3: STEP 6 - Ángulos (Week 7-8)
│  ├─ UI: Ángulo cards (expandible)
│  ├─ Agente Marketing para generar ángulos
│  ├─ Edit & customize ángulos
│  ├─ Backend: creative_angles table + endpoints
│  └─ Time: 5 days
└─ DELIVERY: AI-powered Steps 5-6 con agentes integratos

SEMANAS 8-10: MÓDULO 3 STEPS 7-8 + FINAL POLISH (Fábricas: Imágenes & Videos)
├─ Tarea 1: STEP 7 - Fábrica de Imágenes (Week 8-9)
│  ├─ Midjourney API integration
│  ├─ Prompt generation para Midjourney
│  ├─ Queue management (generation_queue)
│  ├─ Image upload & storage (file system / Supabase storage)
│  ├─ UI: Progress bars, image gallery, download
│  ├─ Backend: image_generations + creative_assets tables
│  └─ Time: 6 days
├─ Tarea 2: STEP 8 - Fábrica de Videos (Week 9-10)
│  ├─ Veo 3.1 API integration (si disponible) o mock
│  ├─ Script/scene generation
│  ├─ Queue management
│  ├─ Video upload & storage
│  ├─ UI: Video player, progress, download
│  ├─ Backend: video_generations + creative_assets tables
│  └─ Time: 6 days
├─ Tarea 3: Final Polish & Testing
│  ├─ End-to-end testing M3 (todos 8 pasos)
│  ├─ Bug fixes & performance optimization
│  ├─ Documentation interna
│  ├─ Deploy a staging environment
│  └─ Time: 4 days
└─ DELIVERY: Fully functional M3 MVP + staging deployment

FASE 1 DELIVERABLES:
✓ Supabase database with 28 tables
✓ Next.js + React frontend architecture
✓ Auth system (signup, login, multi-tenancy)
✓ Language system (dual selectors + variants)
✓ 5 integrated agents (orchestration + logging)
✓ M3 Module: All 8 steps interactive
✓ Midjourney + Veo 3.1 integration
✓ Creative asset storage & management
✓ Staging deployment (testable)
✓ Internal documentation

# FASE 2: EXPAND - MÓDULOS 1 & 4 + META INTEGRATION

Duración: 8 semanas | Hito final: End-to-end platform with research & campaigns

## Objetivos Clave

Integración real con Meta Ads Library API

Implementar M1 completo (Espionaje & Selección)

Implementar M4 completo (Seguimiento de Campañas)

Real-time sync con Meta Ads

Campaign metrics tracking y analytics

Dual-language support para creatives (UI + generation)

Beta testing con 50-100 users

Performance optimization para large datasets

## Desglose por Semana

SEMANAS 11-13: MÓDULO 1 - ESPIONAJE & SELECCIÓN
├─ Tarea 1: Meta Ads Library API Integration
│  ├─ OAuth flow con Meta (cuentas de usuario)
│  ├─ API authentication & token management
│  ├─ Rate limiting & error handling
│  └─ Time: 4 days
├─ Tarea 2: Ad Scraping & Data Ingestion
│  ├─ Background jobs para scrapear ads
│  ├─ Database storage (competitor_accounts, competitor_ads, ad_creatives)
│  ├─ Meta API pagination handling
│  ├─ Scheduling (diario, actualización incremental)
│  └─ Time: 5 days
├─ Tarea 3: M1 UI - Account Selection
│  ├─ UI: Competitor accounts list
│  ├─ Search & filter (plataforma, industria)
│  ├─ Bookmark/save functionality
│  ├─ Backend: account_selection table
│  └─ Time: 3 days
├─ Tarea 4: M1 UI - Ads Library
│  ├─ UI: Ad cards with preview
│  ├─ Metrics visualization (impresiones, engagement)
│  ├─ Comparison tools (side-by-side)
│  ├─ Export/download ads
│  └─ Time: 4 days
├─ Tarea 5: Performance & Optimization
│  ├─ Database indexing optimization
│  ├─ Query performance tuning
│  ├─ Caching strategy
│  └─ Time: 3 days
└─ DELIVERY: M1 fully functional with real Meta data

SEMANAS 13-15: MÓDULO 4 - SEGUIMIENTO DE CAMPAÑAS
├─ Tarea 1: Campaign Creation Interface
│  ├─ UI: Campaign form (nombre, objetivo, budget, datas)
│  ├─ Creative selection from M3
│  ├─ Placement configuration (feed, stories, reels, etc.)
│  ├─ Backend: campaigns + ad_placements tables
│  └─ Time: 3 days
├─ Tarea 2: Meta Ads API - Campaign Sync
│  ├─ Create campaigns via Meta API
│  ├─ Send creative assets to Meta
│  ├─ Real-time bidding & budget management
│  ├─ Status sync (active, paused, completed)
│  └─ Time: 5 days
├─ Tarea 3: Metrics Collection & Display
│  ├─ Background jobs para pull metrics from Meta
│  ├─ Database: campaign_metrics (daily)
│  ├─ UI: Dashboards (realtime metrics, trends)
│  ├─ Charts (impressions, clicks, spend, ROAS, CPA)
│  └─ Time: 5 days
├─ Tarea 4: Analytics & Insights
│  ├─ Agente Leads para análisis de performance
│  ├─ Predictive insights (qué va a mejorar/empeorar)
│  ├─ Recomendaciones automáticas
│  ├─ Database: campaign_performance table
│  └─ Time: 4 days
└─ DELIVERY: M4 fully functional with realtime metrics

SEMANAS 15-18: META INTEGRATION, TESTING & BETA LAUNCH
├─ Tarea 1: End-to-End Integration
│  ├─ Workflow: M1 (research) → M3 (creatives) → M4 (campaigns)
│  ├─ Data flow validation
│  ├─ Error handling & rollback mechanisms
│  ├─ Logging & auditing
│  └─ Time: 4 days
├─ Tarea 2: Beta User Onboarding
│  ├─ Create onboarding flows
│  ├─ Documentation & tutorials
│  ├─ Support systems (chat, email, docs)
│  ├─ Feedback collection tools
│  └─ Time: 3 days
├─ Tarea 3: Internal Testing
│  ├─ QA testing (all 4 modules)
│  ├─ Performance testing (large datasets)
│  ├─ Security testing (penetration, auth)
│  ├─ Load testing (multiple users)
│  └─ Time: 5 days
├─ Tarea 4: Deployment & Monitoring
│  ├─ Production deployment
│  ├─ Monitoring setup (logging, alerts)
│  ├─ Backup & disaster recovery
│  ├─ Beta access control (whitelisting)
│  └─ Time: 3 days
├─ Tarea 5: Launch Beta
│  ├─ Invite 50-100 beta testers
│  ├─ Kickoff communication
│  ├─ Daily monitoring & support
│  ├─ Feedback compilation
│  └─ Time: ongoing
└─ DELIVERY: Stable platform ready for beta users

FASE 2 DELIVERABLES:
✓ Meta Ads Library API fully integrated
✓ M1 (Espionaje & Selección) complete
✓ M4 (Seguimiento de Campañas) complete
✓ Real-time metrics sync from Meta
✓ Analytics & insights (Agente Leads integration)
✓ Complete workflow: Research → Creatives → Campaigns
✓ Production deployment
✓ Beta program (50-100 users)
✓ Performance optimized
✓ Documentation & support systems

# FASE 3: COMPLETION - MÓDULO 2 + REFINEMENT

Duración: 5 semanas | Hito final: Feature-complete platform ready for public launch

## Objetivos Clave

Implementar M2 completo (Creación de Oferta)

UX/UI polish en todos los módulos

Performance optimization

Full language localization (Spanish variants)

Advanced features (A/B testing, custom ángulos)

Enterprise features (team collaboration, API)

Security hardening

Scale testing (1000+ users)

## Desglose por Semana

SEMANAS 19-20: MÓDULO 2 - CREACIÓN DE OFERTA
├─ Tarea 1: Offer Creation Interface
│  ├─ UI: Form para ingresar detalles de oferta
│  ├─ Fields: nombre, descripción, precio, target market
│  ├─ Tipo de oferta selector (course, ebook, app, service)
│  ├─ Backend: product_offers table
│  └─ Time: 3 days
├─ Tarea 2: Positioning & Audience
│  ├─ UI: USP definition, positioning statement
│  ├─ Target audience selectors (age, gender, interests, location)
│  ├─ Benefits listing (functional, emotional, social)
│  ├─ Backend: offer_positioning, target_audience, offer_benefits tables
│  └─ Time: 4 days
├─ Tarea 3: Offer Validation
│  ├─ AI-powered validation (Agente Marketing)
│  ├─ Validation score calculation
│  ├─ Suggestions & improvements
│  ├─ Backend: offer_validation table
│  └─ Time: 3 days
├─ Tarea 4: Integration with M3
│  ├─ Link offers → creative_research
│  ├─ Auto-populate M3 with offer data
│  ├─ Workflow: Create offer → Generate creatives
│  └─ Time: 2 days
└─ DELIVERY: M2 fully integrated with M1-M4

SEMANAS 21-22: POLISH, LOCALIZATION & ADVANCED FEATURES
├─ Tarea 1: UX/UI Polish
│  ├─ Responsive design fixes (mobile, tablet, desktop)
│  ├─ Accessibility audit (WCAG 2.1)
│  ├─ Dark mode support
│  ├─ Animations & transitions refinement
│  └─ Time: 4 days
├─ Tarea 2: Language Localization
│  ├─ Full Spanish support (múltiples variantes)
│  ├─ English localization (base language)
│  ├─ Creatives generation en múltiples idiomas
│  ├─ Dual-language selector testing
│  └─ Time: 4 days
├─ Tarea 3: Advanced Features
│  ├─ A/B testing tool (compare creatives)
│  ├─ Custom ángulo creation
│  ├─ Batch operations (multi-select, bulk actions)
│  ├─ Favoritos & collections
│  └─ Time: 5 days
├─ Tarea 4: Enterprise Features (Premium tier)
│  ├─ Team collaboration (invite members)
│  ├─ Role-based access (admin, editor, viewer)
│  ├─ API keys & webhooks
│  ├─ Custom branding (logo, colors in exports)
│  └─ Time: 5 days
└─ DELIVERY: Feature-complete, polished platform

SEMANA 23: TESTING, SECURITY & SCALE VALIDATION
├─ Tarea 1: Security Hardening
│  ├─ Security audit (OWASP top 10)
│  ├─ Rate limiting & DDoS protection
│  ├─ Data encryption (at rest, in transit)
│  ├─ Compliance (GDPR, CCPA)
│  └─ Time: 3 days
├─ Tarea 2: Performance Optimization
│  ├─ Database query optimization
│  ├─ Frontend bundle size optimization
│  ├─ Caching strategies (server & client)
│  ├─ CDN setup para static assets
│  └─ Time: 3 days
├─ Tarea 3: Scale Testing
│  ├─ Load testing (1000+ concurrent users)
│  ├─ Stress testing (peak loads)
│  ├─ Database scaling validation
│  ├─ API rate limit tuning
│  └─ Time: 3 days
├─ Tarea 4: Final QA
│  ├─ Regression testing (all modules)
│  ├─ Cross-browser testing
│  ├─ Mobile testing (iOS, Android)
│  ├─ Accessibility testing
│  └─ Time: 3 days
└─ DELIVERY: Production-ready, secure, scalable platform

FASE 3 DELIVERABLES:
✓ M2 (Creación de Oferta) complete & integrated
✓ All 4 modules fully polished & functional
✓ Multi-language support (Spanish variants + English)
✓ Advanced features (A/B testing, custom content)
✓ Enterprise features (collaboration, API, webhooks)
✓ Security audit passed
✓ Performance optimized
✓ Scalability validated
✓ Closed beta (200-500 users)
✓ Launch-ready platform

# FASE 4: LAUNCH & GROWTH - PUBLIC BETA → PRODUCTION

Duración: 5 semanas | Hito final: Public launch with revenue generation

## Objetivos Clave

Go-live con público general

Marketing & sales enablement

Customer success & support systems

Revenue tracking & analytics

Onboarding optimization

Community building

Data analytics & insights

Continuous improvement process

## Desglose por Semana

SEMANA 24: LAUNCH PREPARATION
├─ Tarea 1: Marketing Materials
│  ├─ Landing page (optimizado para conversión)
│  ├─ Product video demo
│  ├─ Case studies (beta user examples)
│  ├─ Email sequences (onboarding)
│  └─ Time: 5 days
├─ Tarea 2: Sales Enablement
│  ├─ Pricing page (Starter, Pro, Enterprise, Development)
│  ├─ Feature comparison table
│  ├─ FAQ & help center
│  ├─ Payment integration (Stripe/Mercado Pago)
│  └─ Time: 4 days
├─ Tarea 3: Customer Support Setup
│  ├─ Zendesk/Intercom setup
│  ├─ Chatbot AI (automated first response)
│  ├─ Support documentation
│  ├─ SLA definitions
│  └─ Time: 3 days
├─ Tarea 4: Infrastructure Scaling
│  ├─ CDN global (Cloudflare)
│  ├─ Database replication (backup regions)
│  ├─ Load balancing setup
│  ├─ Auto-scaling configuration
│  └─ Time: 3 days
└─ DELIVERY: Fully ready for public launch

SEMANA 25: PUBLIC BETA LAUNCH
├─ Tarea 1: Beta Release
│  ├─ Public beta announcement
│  ├─ Landing page goes live
│  ├─ Beta access signups
│  ├─ Initial support team ready
│  └─ Time: 3 days
├─ Tarea 2: User Onboarding
│  ├─ Automated email sequences
│  ├─ In-app tutorials & guides
│  ├─ 1-on-1 onboarding calls (top users)
│  ├─ Community Slack channel
│  └─ Time: ongoing
├─ Tarea 3: Monitoring & Support
│  ├─ Real-time monitoring (error rates, performance)
│  ├─ Support team working 24/7 (initial)
│  ├─ Incident response (bugs, API outages)
│  ├─ Daily standup + review
│  └─ Time: ongoing
├─ Tarea 4: Analytics Tracking
│  ├─ Event tracking (signup, module completion, campaign creation)
│  ├─ Cohort analysis
│  ├─ Funnel optimization
│  ├─ User behavior analysis
│  └─ Time: ongoing
└─ DELIVERY: Public beta phase begins with early customers

SEMANAS 26-28: GROWTH & OPTIMIZATION
├─ Tarea 1: Feature Based on Feedback
│  ├─ Collect user feedback (surveys, interviews)
│  ├─ Prioritize feature requests
│  ├─ Quick wins implementation (1-2 week sprints)
│  ├─ Bug fixes & performance improvements
│  └─ Time: ongoing
├─ Tarea 2: Onboarding Optimization
│  ├─ Analyze funnel drop-offs
│  ├─ A/B test landing page variants
│  ├─ Improve M1 onboarding (most complex)
│  ├─ Reduce time-to-first-creative
│  └─ Time: ongoing
├─ Tarea 3: Customer Success
│  ├─ Identify at-risk customers (low usage)
│  ├─ Proactive outreach & training
│  ├─ Case study development (testimonials)
│  ├─ Referral program setup
│  └─ Time: ongoing
├─ Tarea 4: Growth Initiatives
│  ├─ PPC campaigns (Google Ads, LinkedIn)
│  ├─ Content marketing (blog, webinars)
│  ├─ Influencer partnerships
│  ├─ B2B outreach (agencies, consultants)
│  └─ Time: ongoing
├─ Tarea 5: Revenue Optimization
│  ├─ Upsell automation (freemium → paid)
│  ├─ Churn analysis & retention programs
│  ├─ Pricing optimization (A/B testing)
│  ├─ Annual plan promotions
│  └─ Time: ongoing
└─ DELIVERY: Sustainable growth & revenue generation

FASE 4 DELIVERABLES:
✓ Public beta launch
✓ Marketing website & landing pages
✓ Sales infrastructure (payments, invoicing)
✓ Customer support system (24/7 availability)
✓ Analytics & monitoring dashboards
✓ Onboarding automation
✓ Feature feedback loop
✓ Community & user base
✓ Revenue tracking & metrics
✓ Continuous improvement process
✓ Roadmap for next iterations

# RESUMEN EJECUTIVO

TIMELINE TOTAL: 28 SEMANAS (~6.5 MESES)

┌────────────────────────────────────────────────────────────────────┐
│ FASE 1: MVP (Semanas 1-10)                                        │
├────────────────────────────────────────────────────────────────────┤
│ Módulos: M3 (completo) + Infrastructure + 5 Agentes               │
│ Deliverables: Staging MVP, M3 fully functional                    │
│ Users: Internal testers                                           │
│ Key Metrics: M3 end-to-end working, <200ms latency                │
│ Go/No-Go Gate: 95% test pass rate, no critical bugs               │
└────────────────────────────────────────────────────────────────────┘

┌────────────────────────────────────────────────────────────────────┐
│ FASE 2: EXPAND (Semanas 11-18)                                    │
├────────────────────────────────────────────────────────────────────┤
│ Módulos: M1 (complete) + M4 (complete) + Meta API                 │
│ Deliverables: Production platform, real Meta data, beta program   │
│ Users: 50-100 beta testers                                        │
│ Key Metrics: Meta sync 99.9% uptime, <5min metric lag             │
│ Go/No-Go Gate: Beta user retention >70%, NPS >40                  │
└────────────────────────────────────────────────────────────────────┘

┌────────────────────────────────────────────────────────────────────┐
│ FASE 3: COMPLETION (Semanas 19-23)                                │
├────────────────────────────────────────────────────────────────────┤
│ Módulos: M2 (complete) + Polish + Advanced Features                │
│ Deliverables: Feature-complete, secure, scalable platform         │
│ Users: 200-500 closed beta testers                                │
│ Key Metrics: All 4 modules >95% uptime, <100ms p95 latency        │
│ Go/No-Go Gate: Security audit passed, scale tested to 1000+ users │
└────────────────────────────────────────────────────────────────────┘

┌────────────────────────────────────────────────────────────────────┐
│ FASE 4: LAUNCH & GROWTH (Semanas 24-28)                           │
├────────────────────────────────────────────────────────────────────┤
│ Módulos: Public release + Growth optimization                     │
│ Deliverables: Live platform, paying customers, content marketing  │
│ Users: Public (unlimited)                                         │
│ Key Metrics: Launch day signups, customer acquisition cost, MRR   │
│ Go/No-Go Gate: First 50 paying customers, <$50 CAC goal           │
└────────────────────────────────────────────────────────────────────┘

TEAM STRUCTURE:
├─ Frontend: 2 developers (Next.js, React, Tailwind)
├─ Backend: 2 developers (Node.js/Python, Supabase, APIs)
├─ AI/Agents: 1 developer (Claude SDK, agent orchestration)
├─ DevOps/Infrastructure: 1 engineer (Supabase, Meta APIs, scaling)
└─ Product Manager: 1 (roadmap, prioritization, stakeholder management)

TOTAL: 7 FTE over 28 weeks

BUDGET ESTIMATE (Approximate):
├─ Salaries (7 FTE × 28 weeks): $280,000 - $350,000
├─ Infrastructure (Supabase, APIs, CDN): $20,000
├─ Marketing & Launch: $30,000
├─ Tools & Services (Slack, Linear, Figma, etc.): $5,000
└─ TOTAL: ~$335,000 - $405,000

RISKS & MITIGATION:
├─ Risk: Meta API changes/restrictions
│  └─ Mitigation: Monitor Meta changelog, build abstraction layer
├─ Risk: Midjourney/Veo 3.1 API unavailable
│  └─ Mitigation: Have backup image generation service ready
├─ Risk: High churn in beta phase
│  └─ Mitigation: Dedicated customer success team, weekly check-ins
├─ Risk: Performance issues at scale
│  └─ Mitigation: Load testing in Phase 2-3, database optimization
└─ Risk: Regulatory changes (AI, data privacy)
   └─ Mitigation: Legal review, GDPR/CCPA compliance from start

SUCCESS METRICS:
├─ Phase 1: M3 fully working, 0 blockers for Phase 2
├─ Phase 2: Beta retention >70%, NPS >40
├─ Phase 3: 95%+ platform uptime, <100ms latency
└─ Phase 4: First 100 paid customers, $10k+ MRR within 3 months